## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## EXAMPLE
PROJECT PLAN
PROJECT NAME | DATA ANALYTICS
PROJECT MANAGER | SURAJ MANE
PROJECT SCOPE
PROJECT START DATE | 2023-07-01
PROJECT END DATE | 2023-09-30
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2023-07-01 | 2023-07-04 | 4 | COMPLETED
| 1.2 Recruit a team |  | 2023-07-05 | 2023-07-10 | 5 | COMPLETED
| 1.3 Create a project charter |  | 2023-07-11 | 2023-07-16 | 6 | COMPLETED
| 1.4 Requirement gathering |  | 2023-07-17 | 20/07/02023 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2023-07-21 | 2023-07-31 | 10 | COMPLETED
| 2.2 Baseline project plan |  | 2023-08-01 | 2023-08-04 | 4 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2023-08-05 | 2023-08-09 | 4 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2023-08-11 | 2023-08-15 | 4 | COMPLETED
| 3.2 Build |  | 2023-08-16 | 2023-08-21 | 5 | COMPLETED
| 3.2.1 Features |  | 2023-08-22 | 2023-09-25 | 33 | COMPLETED
Data Collection
Data Cleaning and Preprocessing
Exploratory Data Analysis (EDA
Data Transformation and Feature Engineering
Data Modeling
Model Evaluation
Data Visualization and Interpretation
Reporting and Presentation
| 3.3 Testing |  | 2023-09-28 | 2023-09-29 | 1 | COMPLETED
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2023-09-30 | 2023-09-30 | 1 | COMPLETED